## Summary
TAYYIBT HOMES — FREELANCE DEVELOPMENT COST ESTIMATE (EGYPT)
All rates in USD · Egyptian freelance market · June 2026
PROJECT OVERVIEW
Project | Tayyibt Homes — Real Estate & Location Intelligence Module
Platform | NestJS API · Next.js Web · Flutter Mobile · FastAPI AI
Duration | 24 Weeks (4 phases × 6 weeks each)
Team Location | Egypt (Remote Freelancers)
Currency | USD — Egyptian market international rates
COST SUMMARY — THREE TEAM OPTIONS
Team Option | Profile | Total Hours | Avg Rate ($/hr) | Phase 1 | Phase 2 | Phase 3 | Phase 4 | TOTAL COST
Budget Team | Mid-level only | 1720 | 22 | 7810 | 10010 | 9240 | 10560 | 37620
Balanced Team | Senior + Mid mix | 1720 | 30 | 10650 | 13680 | 12600 | 14400 | 51330
Premium Team | Senior specialists | 1720 | 42 | 14910 | 19140 | 17640 | 20160 | 71850
PHASE TIMELINE
Phase | Weeks | Scope | Key Deliverables | Backend | Frontend | Flutter | AI/Python | Total Hrs
Phase 1 | 1–6 | Foundation | DB schema, auth, basic map embed, dev portal application | 120 | 60 | 40 | 20 | 320
Phase 2 | 7–12 | Listings & Map | Live map pins, listing CRUD, mobile map screen, save feature | 100 | 100 | 120 | 20 | 410
Phase 3 | 13–18 | AI Engine | Location AI suggestions, couple-alignment score, heatmap | 60 | 80 | 80 | 120 | 400
Phase 4 | 19–24 | Future Vision & Analytics | Timeline slider, dev analytics dashboard, monetisation | 80 | 100 | 80 | 60 | 440
TOTAL |  |  |  | 360 | 340 | 320 | 220 | 1570
Notes: Hours above cover Backend + Frontend + Flutter + AI only. QA (160h), UI/UX (130h), DevOps (70h), PM (120h) are included in full cost sheets.

## Roles & Rates
EGYPTIAN FREELANCE DEVELOPER RATES — BY ROLE & SENIORITY
Market rates sourced from Upwork, Mostaql, LinkedIn Egypt, and direct market surveys · June 2026 · USD/hour
Role | Skill / Stack | Junior ($/hr) | Mid-level ($/hr) | Senior ($/hr) | Budget Rate Used | Balanced Rate Used | Premium Rate Used
Backend Developer | NestJS · TypeScript · PostgreSQL · Redis | 12 | 22 | 42 | 22 | 32 | 42
Frontend Developer | Next.js · React · Tailwind CSS | 10 | 20 | 38 | 20 | 29 | 38
Mobile Developer | Flutter · Dart · Riverpod · Maps SDK | 12 | 22 | 40 | 22 | 31 | 40
AI / Python Developer | FastAPI · scikit-learn · NumPy · GeoPandas | 14 | 25 | 48 | 25 | 36 | 48
UI/UX Designer | Figma · Mobile & Web · Map UI | 10 | 18 | 32 | 18 | 25 | 32
DevOps Engineer | Docker · Nginx · GitHub Actions · AWS | 12 | 22 | 40 | 22 | 31 | 40
QA Engineer | Postman · Cypress · Flutter test | 8 | 15 | 28 | 15 | 21 | 28
Project Manager | Agile · Scrum · Technical PM | 10 | 18 | 35 | 18 | 25 | 35
LEGEND
Blue rate | Budget Team |  | Mid-level freelancers only — lowest cost, suitable for MVP / tight budget
Orange rate | Balanced Team |  | Mix of senior leads + mid-level devs — best value for quality delivery
Dark red rate | Premium Team |  | Senior specialists across all roles — highest quality, fastest delivery
Source: Upwork Egypt profiles, Mostaql.com, LinkedIn Egypt job posts, direct community surveys — June 2026. Rates reflect experienced remote-capable freelancers, not absolute market minimum.

## Phase Breakdown
HOURS BREAKDOWN BY PHASE & ROLE
Hours estimated for each role across all four delivery phases
Role | Phase 1 (Wks 1–6) Foundation | Phase 2 (Wks 7–12) Listings & Map | Phase 3 (Wks 13–18) AI Engine | Phase 4 (Wks 19–24) Future Vision | TOTAL HOURS
Backend Developer | 120 | 100 | 60 | 80 | 360
Frontend Developer | 60 | 100 | 80 | 100 | 340
Mobile (Flutter) Developer | 40 | 120 | 80 | 80 | 320
AI / Python Developer | 20 | 20 | 120 | 60 | 220
UI/UX Designer | 40 | 40 | 20 | 30 | 130
DevOps Engineer | 20 | 10 | 10 | 30 | 70
QA Engineer | 20 | 40 | 40 | 60 | 160
Project Manager | 30 | 30 | 30 | 30 | 120
TOTAL HOURS | 350 | 460 | 440 | 470 | 1720
PHASE WORKLOAD DISTRIBUTION (% of total hours per role)
Role | Phase 1 % | Phase 2 % | Phase 3 % | Phase 4 % | Check
Backend Developer | 33.33% | 27.78% | 16.67% | 22.22% | 100%
Frontend Developer | 17.65% | 29.41% | 23.53% | 29.41% | 100%
Mobile (Flutter) Developer | 12.5% | 37.5% | 25% | 25% | 100%
AI / Python Developer | 9.091% | 9.091% | 54.55% | 27.27% | 100%
UI/UX Designer | 30.77% | 30.77% | 15.38% | 23.08% | 100%
DevOps Engineer | 28.57% | 14.29% | 14.29% | 42.86% | 100%
QA Engineer | 12.5% | 25% | 25% | 37.5% | 100%
Project Manager | 25% | 25% | 25% | 25% | 100%

## Detailed Cost
DETAILED COST BREAKDOWN — ALL THREE TEAM OPTIONS
Cost = Hours × Hourly Rate per role · Rates from 'Roles & Rates' sheet · All figures in USD
Role | P1 Hrs | P2 Hrs | P3 Hrs | P4 Hrs | Total Hrs | Budget Rate | Budget Cost | Balanced Rate | Balanced Cost | Premium Rate | Premium Cost
Backend Developer | 120 | 100 | 60 | 80 | 360 | 22 | 7920 | 32 | 11520 | 42 | 15120
Frontend Developer | 60 | 100 | 80 | 100 | 340 | 20 | 6800 | 29 | 9860 | 38 | 12920
Mobile (Flutter) Developer | 40 | 120 | 80 | 80 | 320 | 22 | 7040 | 31 | 9920 | 40 | 12800
AI / Python Developer | 20 | 20 | 120 | 60 | 220 | 25 | 5500 | 36 | 7920 | 48 | 10560
UI/UX Designer | 40 | 40 | 20 | 30 | 130 | 18 | 2340 | 25 | 3250 | 32 | 4160
DevOps Engineer | 20 | 10 | 10 | 30 | 70 | 22 | 1540 | 31 | 2170 | 40 | 2800
QA Engineer | 20 | 40 | 40 | 60 | 160 | 15 | 2400 | 21 | 3360 | 28 | 4480
Project Manager | 30 | 30 | 30 | 30 | 120 | 18 | 2160 | 25 | 3000 | 35 | 4200
TOTAL | 350 | 460 | 440 | 470 | 1720 |  | 35700 |  | 51000 |  | 67040
COST BY PHASE
Phase | Description | Hours |  | Budget Cost |  | Balanced Cost |  | Premium Cost
Phase 1 | Foundation (Wks 1–6) | 320 |  | 7810 |  | 10650 |  | 14910
Phase 2 | Listings & Map (Wks 7–12) | 410 |  | 10010 |  | 13680 |  | 19140
Phase 3 | AI Engine (Wks 13–18) | 400 |  | 9240 |  | 12600 |  | 17640
Phase 4 | Future Vision & Analytics (Wks 19–24) | 440 |  | 10560 |  | 14400 |  | 20160
GRAND TOTAL | All 24 Weeks | 1570 |  | 37620 |  | 51330 |  | 71850

## Recommendation
TEAM RECOMMENDATION & RISK NOTES
RECOMMENDED: Balanced Team · Estimated Total: ~$51,330 USD
Why Balanced? | The Balanced Team uses senior developers as technical leads on the most complex components (AI engine, map integration, NestJS architecture) while mid-level developers handle routine CRUD, UI screens, and testing. This gives you quality output at roughly 40% less than an all-senior team, with manageable risk.
Suggested Team Composition | 1 Senior Backend (NestJS lead) · 1 Mid Frontend (Next.js) · 1 Mid Flutter · 1 Senior AI/Python (location engine) · 1 Mid UI/UX · 1 Mid DevOps (part-time) · 1 Junior-Mid QA · 1 Part-time PM
How to hire in Egypt | Best platforms: Upwork (Egyptian profiles, filter by 90%+ JSS), Mostaql.com (Arabic platform, strong for Egyptian devs), LinkedIn Egypt. Always request a paid 2–3 hour test task before committing to a long engagement.
BUDGET OPTION · ~$37,620 USD — When to choose
Suitable if | You have a tight runway and need to launch Phase 1–2 only (map + listings). Avoid using Budget Team for the AI Engine phase (Phase 3) — the location intelligence logic is complex and under-experienced Python devs will create technical debt.
Risk | Slower velocity, more bugs, more review cycles. Budget ~20% extra time buffer.
PREMIUM OPTION · ~$71,850 USD — When to choose
Suitable if | Time-to-market is critical (e.g., investor demo in 4 months) or you need enterprise-grade code quality from day one with minimal supervision overhead.
Risk | Highest cost. Harder to find 8 senior Egyptian freelancers simultaneously — expect 3–4 weeks of sourcing time. Consider a hybrid: senior for AI + Balanced elsewhere.
CONTINGENCY & HIDDEN COSTS
Buffer | Add 15–20% contingency for scope creep and revision cycles.
Map API costs | Mapbox: ~$0.50/1,000 tile requests. Budget $200–500/month for dev + staging.
Third-party APIs | Google Maps Platform or Mapbox GL JS license. Budget $100–300/month prod.
Infrastructure | Existing Docker/VPS setup covers this — minimal additional cost.
Legal / Contracts | Use a written contract with milestone-based payments. Egyptian freelancers commonly accept 30% upfront / 70% on delivery per phase.
Payment | Wise (TransferWise) or PayPal are most common for USD → Egypt remittance.